## Slide 1
DISCOVER
Phase 1 · Inventory · WSDL audit
MIGRATE
Phase 2 · Java 21 · Spring Boot 4
DEPLOY
Phase 3 & 4 · AKS · Istio · Harness
AI-ASSISTED MIGRATION
.NET WCF
to Java Spring Boot
A Four-Phase AI-Powered Framework
Azure · AKS · Istio · Harness · GitHub Copilot
CONFIDENTIAL · INTERNAL USE ONLY

## Slide 2
THE CHALLENGE
Legacy .NET WCF — Why We Must Migrate
End of Life
WCF is frozen — no new features, security patches limited, Windows-only hosting locks us out of cloud-native infrastructure.
SAP SOAP Coupling
Tight coupling via auto-generated Reference.cs proxies. Any SAP WSDL change risks breaking the entire integration layer silently.
No Cloud Scale
IIS/Windows hosting cannot run on AKS. No horizontal scaling, no Istio mesh, no Harness pipelines. Cannot meet our Azure strategy.
The answer: a structured AI-assisted migration to Java 21 + Spring Boot 4, running natively on AKS with full Istio mesh observability.

## Slide 3
THE SOLUTION
A Four-Phase AI-Powered Migration Framework
01
Phase 1
Discovery
Service inventory · WSDL audit · Risk scoring
02
Phase 2
App Migration
Java 21 · Spring Boot 4 · SAP clients · Tests
03
Phase 3
Infrastructure
Dockerfile · Helm · AKS · Istio · Harness
04
Phase 4
Cutover
SAP validation · Strangler Fig · Decommission
GitHub Copilot + Azure OpenAI · AI-generated prompts drive 70-80% of repetitive code and config across all four phases

## Slide 4
TECHNOLOGY STACK
From Legacy Windows to Cloud-Native
FROM · Legacy Stack
— .NET WCF (Windows Communication Foundation)
— SOAP/WSDL services with auto-generated proxies
— IIS / Windows Server hosting
— web.config XML configuration
— Manual deployments
— No observability, no mesh, no auto-scaling
TO · Target Stack
Language
Java 21 (records, sealed types, switch expressions)
Framework
Spring Boot 4 · Spring WS · Wss4j
Cloud
Azure · AKS · Azure Container Registry
Mesh
Istio · mTLS · VirtualService · Kiali
Pipeline
Harness · Helm 3 · GitOps
AI Tools
GitHub Copilot · Azure OpenAI · Prompts library

## Slide 5
PHASE 1
Discovery & Analysis
Weeks 1–3 · AI-led
1.1 Service Inventory
Copilot @workspace scans every .svc file, [ServiceContract], [DataContract] and Reference.cs to produce the migration manifest JSON.
1.2 Dependency Graph
Maps internal WCF-to-WCF calls and shared utilities. Drives microservice boundary decisions and identifies circular dependencies.
1.3 WSDL Audit
Deep audit of every SAP WSDL — operations, types, security schemes, drift vs Reference.cs. Builds the WSDL registry for Phase 2.
1.4 Risk Classification
Scores every service Green / Amber / Red on 11 factors. Produces the sprint sequencing plan for Phase 3 full migration.
OUTPUT · manifest.json · dependency-graph.json · wsdl-registry.json · risk-classification.json · sprint-plan.json

## Slide 6
PHASE 2
Application Migration
Pure Spring Boot code · No infrastructure · AI-led translation
2.1
WSDL → Java Stubs
jaxb2 replaces
svcutil.exe
2.2
DTO Translation
[DataContract]
→ Java records
2.3
Business Logic
.svc.cs →
@Service
2.4
SAP Client
WebServiceTemplate
+ Wss4j
2.5
Exception Map
FaultException
→ RuntimeException
2.6
Tests
JUnit 5 +
Cloud Contract
2.7
Common Lib
Shared beans
& filters
Critical rule:
Prompt 2.3-A (pre-translation analysis) runs BEFORE any Java is written. It documents every business rule, SAP field mapping and financial calculation. AI generates code — engineers validate semantics. Every service passes the Prompt 2.R review gate before merge.
OUTPUT · @Service classes · @RestController endpoints · SAP clients · contract tests · common-lib module

## Slide 7
PHASE 3
DevOps & Infrastructure
Runs in parallel with Phase 2 · Platform team owns this phase
Dockerfile
Multi-stage build · Java 21 distroless · non-root UID 1000 · OCI labels
Azure Container Registry
Immutable tags [sha-7] · Trivy scan on push · AcrPull via managed identity
Helm Library Chart
Shared templates for Deployment, HPA, PDB, SecretProvider · per-service values.yaml thin override
AKS Configuration
Namespaces · RBAC · NetworkPolicy default-deny · Azure Workload Identity · Key Vault CSI
Istio Service Mesh
VirtualService + DestinationRule (java-v1 / dotnet-v1 subsets pre-wired) · STRICT mTLS · Circuit breaker
Harness Pipeline
Build → Test → Push → Dev (auto) → Staging (approval) → Prod (change ticket + approval)
Gate: All services pass Prompt 3.R (20-item security · reliability · deployment · observability checklist) before Phase 4

## Slide 8
PHASE 4
Strangler Fig — Zero-Downtime Cutover
Stage 0
.NET 100%
Baseline
(no action)
Stage 1
.NET 90%
Canary
48 h observe
↩ rollback < 30s
Stage 2
.NET 50%
Java 50%
Parity
48 h observe
↩ rollback < 30s
Stage 3
Java 100%
Full cutover
72 h observe
↩ rollback < 30s
Advance criteria per stage:
Error rate < threshold · No pod restarts · SAP fault rate stable · p99 latency within SLO · Senior engineer sign-off
Powered by:
Istio VirtualService weight patches · PrometheusRule alerts · Grafana dashboard · AI-generated rollback runbook & decision tree

## Slide 9
AI TOOLING
GitHub Copilot as the Migration Engine
52
AI prompts
across 4 phases
one reusable
instruction file
per phase
Phase 1
@workspace scans solution for WCF contracts, operations, SAP proxies, web.config endpoints. Produces JSON manifest.
Phase 2
Translates .svc.cs business logic to @Service, generates records, SAP clients, unit tests and contract stubs.
Phase 3
Generates Dockerfile, Helm library chart, Istio VirtualService/DestinationRule, Harness pipeline YAML.
Phase 4
Generates integration tests, parity scripts, rollback runbooks, Prometheus alert rules, Grafana dashboards.
Principle: AI handles repetitive pattern-based generation. Engineers own business logic validation, SAP semantics and architectural decisions.

## Slide 10
TIMELINE
Phased Delivery — Risk-Tiered Sprint Sequencing
Wk 1–3
Phase 1
Discovery
& Analysis
Wk 4–9
Phase 2+3
App + Infra
(parallel)
Wk 10–14
Green Svcs
4 services
Sprint 1–2
Wk 15–20
Amber Svcs
6 services
Sprint 3–4
Wk 21+
Red Svcs
Remaining
Sprint 5–6
Green tier: 0–4 pts · simple CRUD · AI-led · 1-2 sprints
Amber tier: 5–9 pts · multiple SAP ops · engineer + AI · 3-4 sprints
Red tier: 10+ pts · financial calc · senior engineer · sprint 5–6
Strangler Fig cutover — per service during Phase 3/4 delivery window
10%
Stage 1
Canary · 48h
50%
Stage 2
Parity · 48h
100%
Stage 3
Full · 72h
Decom.
.NET retired
30d window
Each stage requires: SAP integration tests pass · Response parity check pass · Pre-cutover readiness checklist signed off · Rollback runbook reviewed

## Slide 11
KEY BENEFITS
Why This Approach Wins
70%
Less manual code
AI generates boilerplate, stubs, tests and infra config. Engineers focus on business logic and SAP semantics.
0
Big-bang risk
Strangler Fig pattern with Istio weights means any service can roll back to .NET in under 30 seconds.
52
Reusable prompts
A version-controlled prompt library across all 4 phases. Future migrations plug in at Phase 1 and reuse everything.
100%
SAP parity tested
Response parity comparison script validates every field. 7 SAP edge-case categories tested before any traffic shifts.
1
Helm library chart
Every service shares one library chart. Adding a new service is a 20-line values.yaml. Consistency enforced.
mTLS
Enforced everywhere
Istio STRICT mTLS from day one. AuthorizationPolicy restricts ingress per service. Key Vault for all credentials.

## Slide 12
NEXT
STEPS
01
Kick off Phase 1 — provision IDE access to .NET solution and run Prompt 1.1-A
02
Identify two Green-tier pilot services for Phase 2 proof-of-concept
03
Platform team begins Phase 3 infrastructure in parallel (Helm library, ACR, AKS namespaces)
04
Schedule SAP team alignment — sandbox access and credential provisioning for Phase 4
The Framework
Is Ready
Deliverables ready to commit to .github/:
phase1-copilot-instructions.md
9 discovery & analysis prompts
phase2-copilot-instructions.md
14 application migration prompts
phase3-copilot-instructions.md
14 DevOps & infrastructure prompts
phase4-copilot-instructions.md
15 integration & cutover prompts
"The framework built in Phase 2 is the real deliverable — not just the pilot services. Every hour invested in the Helm library, common-lib and prompt library pays back multiplied across every service in the full migration."